Clip meeting July 20, 2005

at MSU

# Planning RAMS model runs

- Need to get benchmark for NCAR, Nathan has benchmarks for the other 3 machines.

- Timing: need to factor in post-processing time.  So have around 10 months to do initial runs. Need to have RAMS results and the resultant NPP (crops, rangelands, natural ecosystem) responses by summer next year to take to East Africa to present to expert systems to obtain LU & community responses to climate change.  Then will later have to do additional follow-up and feedback runs. And write up.

- According to proposal:

  - Dynamic climate, no LUC (with our Clipcover & LAI curves)

  - Dynamic land, static climate

  - Dynamic climate, LU scenarios (high, low, most plausible)

  - Feedback every decade (HAVE to do this, close the loop)

- There are additional questions that would be of interest, for example which land cover class change most affects climate change, comparing the effect of different land cover classification schemes, and whether spatial distribution of LUC or absolute amount of LUC affects climate. Bryan & Qi/ Jianjun especially have questions they would like to pursue. These would be additional questions beyond what is in the proposal, and we would need to schedule supplemental time to look at them.

- Approaches to the runs:

  - Snapshot high resolution (16 km)

  - Decadal low resolution (64 km): jumping ahead: 2005-15, 2045-55, 2085-2095.  If possible depending on time available, add a decade.

  - Pros & cons of constantly running vs. time slice?

- Meeting to finalize the run priorities & time table:  need to have climate & land people; will schedule asap.

## Other Climate

2.GCM data for boundary: Nathan is downloading (CCSM3), and working out how to convert the files (Brent can help?).

3.Nathan: problem that soil moisture over-influences climate in RAMS. Currently working on RAMS simulation 4 months of 2000 comparing RAMS output with TRMMS data.  Thinks that we have to cut off the tweaking (calibrating RAMS to East Africa data) due to time requirements of project.

4. Clair and Declan sent an email in June with an update of their activity, including a comparison of two gridded historical climate datasets for East Africa (CRU and newly released GPCC). They determined that the GPCC was better for trend analyses.  They received new Uganda station data from Magezi. They will be working on the comparison of GCMs for EA, and using GCM output to perturb their weather generator to determine effects on seasonality, and SOI and IOD.

## NPP

4.Alagarswamy needs a decade of daily data (solar radiation, min/max temp, precip) from RAMS to do his projections of crop production.

5.ERA 40 vs. CRU gridded historical climate datasets.  We received the ERA40 data, but there is a problem with the data when compared to observed station data, and it doesn’t have the variables required by the crop-climate models. So Jeff & Alagarswamy decided that they couldn’t use it. The CRU data (0.5 degree) is downloaded. Dave Lusch will come by Friday to look at it and import and georeference the data. CRU has monthly means & Alagarswamy can run a program from Phil to get estimated daily.  Also Alagarswamy will follow up with Clair & Declan about GPCC data that they mentioned in an email.

6.We’ve received Uganda farm field surveys and other field information, and agricultural research articles from John Owour at ILRI. They will be helpful. John is now in Tanzania collecting similar information for Clip.

7. Ruth has sent email updates; she is finishing her first task of running the LPJ vegetation model (1900-2002) calibrated with Phil’s daily historical weather data. LPJ will be run later with RAMS output.  She is preparing to do her next task of comparing GCM output for East Africa with Clair and Declan.

## Bryan: LU modeling

Bryan will have three students working with him on various projects including/ particularly CLIP (two terrific fellowship students, Deepak Ray, his wife (didn’t catch name), and *).

7.Amelie Davis (a fellowship student next year, too): she running and moderating LTM. She has added the gridded UN population density projection data. LTM is moving towards being a rule-based model, which will be useful for incorporating the expert systems info. Bryan also prepared a hydrological model that will be linked to LTM.

8.MABEL: started working on her but had to drop her, will start again in 1 ½ wks

9.Kostas will work a bit on Mabel (conceptual aspects) & Baysian things for his dissertation

10. LTM could use better climate data. The current data, Corbett’s ACT data, has too big influence on LTM probably because not closely correlated with other variables, so may not be reliable. The CRU data may be useful except that it is so coarse.

6.Uncertainty paper with Marian Huebner: fall semester

7.Role playing paper with David Campbell: fall semester

## Land use & cover

8.Jing’s LAI MODIS phenological splines: she has averaged 4 years of data into 0.1 degree cells for the region by Clipcover class. The resultant phenological curves weren’t very satisfying, lots of unexpected variability especially in the forest classes.  The curves for a grassland class in a dry area was pretty good. So, thought that problem could be due to cloud cover & water (labeled zero) somehow still in the dataset. Initial tests removing the zeros improved the result. So, she will re-do the averages to make new curves.

9.Sarah: will incorporate better climate & elevation, land use/cover data into NDVI co-kriging spatio-temporal analysis of vegetation/ climate/ land use.

10.Sigismond: looking at conflict over land & water resources in TZ, how affecting land use.  He received lots of information from Yanda and Misana.

11.Ben/ Nate/ Jenny:

- Will be analyzing trends in 1982-2004 NDVI (controlled for rainfall) in two savanna areas to see impact of land management on NDVI.

- Fuelwood study:

  - Received a good literature review from Sam Mugisha on fuelwood impacts in Uganda, and a large research report from Misana on the same for Tanzania.

  - Ben and Nate are preparing higher resolution datasets for running Bob Schole’s spatially-explicit model (based on population, tree cover, climate etc) on the impact of fuelwood collection on forest cover. We need to ask Bryan what would LTM include re declining biomass from woodfuel harvesting?

- Urbanization study: received good input from Yanda on drivers/ impacts of urbanization in Tanzania, and Ben has revised the paper.

## General

7.Publications: need to send info to David about what papers we have submitted, in press, conference papers, etc. for upcoming NSF report.

8.Manly Miles: space auditors coming. We need to show that we’re using our space well & can justify the need for more space