CLIP/NSF Meeting Notes (Sept 19-21, 2003)

Aim: define the project activities for the next 12-24 months.

- Combine the components of the project, up-and-running.

- Need to understand what each of the group members is doing, so that we can coordinate activities.

- Where the project fits on the broader activities and objects.

Review of the Project Activities.

- The Project’s flow diagram (slide) – the one from the proposal, p.3

- Linkages and feedbacks between project activities (Table 1 in proposal, p.5)

Website Discussion

- FTP site?

- Power-point & data sharing

- Flyer

- Poster available

- Publicly available data, or meta-data (data via email or other method)?

GROUP DISCUSSION – Land Use Change

- RAMS → Regional Climate Model

- LTM → Land Transformation Model

- MABEL → Agent-Based Model

- NPP → Net Primary Productivity

- RPS → Role Playing Simulation

- BBN → Bayesian Belief Networks

- Scaling-up: km → 40 km.

  - Representativeness of case studies

  - Degree of LUC needed for CE

    - Eg., 10%Δ-where/when

    - Eg., urbanization + rings of ag + deforestation, or Von Thuen

    - Eg., capitalism

    - Eg., peace

- An important issue is how we parameterize the models to coordinate in compatible time-steps?

- How the people change their LU/LC behavior?

  - Policy Adjudication 5-10 yrs

  - Econ., population changes (↑) decline on coffee (eg) gradual → tipping point.

  - What’s important from the climate LU/LC modelers perspective is not socio-econ changes in general, but only these socio-econ changes that affect the LU/LC changes.

  - Then the issue in question is the context of these changes in temporal, geographical (spatial), and behavioral vantage points.

  - On the other hand, we have to keep in mind that the challenge is not to loose the big image (eg, the whole study area, not just the case-study areas).

NPP Activities:

- Met → LTM → LC for RAMS

- Regional LTM / Exp sys ? with MPP

- Blue Case Sequence (could start now)

- NPP  → Reg + cases

- Reactions to outputs, RPS, interviews (MABEL)

Activities Sequence:

- NPP → LC → RAMS		Phil T. Jeff; Qi, Dave L

(Calibration: LU → LC)			MID 2004 → compare NPP model parameters

w/ RS par

- NPP Expert → LTM → LC → RAMS

  - What does this means with broad categories of LU and human groups?

  - What other variables are coming into play? (eg, roads, soils, etc.)

  - In the part (expert→LTM) there should be an evaluation stage that validates (and calibrates the model)

  - Bookend scenarios: -1sd, x, +1sd

  - Relative strength of drivers/country/time period/place

  - MC (multi-criteria) evaluation of experts for LTM

  - On the RAMS side, what is the level of resolution? Projections?

  - Discussion about scenario properties:

    - Emergent (“noise”)

    - Resilient (“continuous”)

    - Shock (“A”, eg, drought, SAP, tech, GMO)

    - Response (“local, generic”)

  - Core (Tz, Ug, Ke) versous Boundary (Za, Zi, Co)

    - Broad LU/LC cover change

    - ¼ hot spots of change → experts why?

- Bluecase

  - future based on past

  - if inputs ↓ - ? NPP

  - bookend motif? Of amount of LUC%?

  - Land cover classes

GROUP DISCUSSION: Communicating Results from Climate Group

An Overview

  - Step 1: initial perturbation (CO2, forced climate change, externally imposed land cover change)

  - Step 2: climate response to climate-induced land use change

  - The first step comes from a base-case, while step two is a higher hierarchy of climate interactions.

  - Step 2 is a unique scenario, while step 1 is not a unique scenario.

Key-points:

  - Possible hiring plans/use of RegCM – may delay initial model runs, but may give large gains in terms of model.

  - Boundary conditions – Hadley model data is available for 1961-90, 2070-2100.

  - Feedback, temporal aspects, time lags – annual update to land cover is too often. Updates may be better if based on a good sample of climate (decade).

  - BIOME III – Ruth

    - Gives some biome type based on precip., temp., and radiation.

    - Validation may need to be done by others.

  - Activity II: Ecosystems Productivity

1. Agricultural		2. Ecosystem

    - Prepare model simulations, collect process necessary weather, auxiliary data (Eco: Dec 03, Ag: Sum 04)

    - Validate simulations, run with historical data, process/analyze output (Eco: SUM 04, Ag. WIN 04)

    - Run sims with projected future data, analyze output, interactive sims with LULC (Eco: WIN 04, Ag: FAL 06).

# Text boxes

NPP

Crop Range

Land

Cover

Case

Studies

Surrogate

Variables

MABEL

LTM

OUTPUT

Assessment

Case

RPS

Key Info

RAMS

Scaling

up

1 km?

Albedo, LAI, SR